## SPRINT_BACKLOG
SPRINT 1 BACKLOG

ID	User Story	Tasks	Owner	Status	Day 1	Day 2	Day 3	Day 4	Day 5	Day 6	Day 7	Estimated effort
US001	As a customer / I need to be able to use a computer on the cloud / So that I have a dedicated work environment	Create VPC and Subnet using / Terraform	Shatta	Done	2					5
		Create an instance	Shatta	Done		2
		prepare the instance for remote / Connection	Shatta	Done		1
US002	As a customer / I need to be able to Backup the computer / So that I can return to same state in the future.	make an image from the instance	Ali	Done			5					5
US003	As a customer / I need to stop the computer and make a new / one from the backup / So that I work on a new environment with that / Old state	stop the old instance	Ali	Done				1				2
		create an instance from the image	Ali	Done				1
US004	As a customer / I need to be able to automate the creation and / backup process / So that I do not need to concern myself with / backup.	Create Composer on GCP using / Terraform	Shatta	Done					4	3		12
		Create a DAG on the composer to / Automate the task	Ali	Doing					3	2
Total					2	3	5	2	0	0	0	12

## PROJECT_DETAILS
PROJECT NAME	GCP Composer & DAG demo project
PRODUCT OWNER	Hadi Lotfy
SCRUM MASTER	Merit Mekhail
VERSION	V1.0